## Defect_Log
Defect ID | Title | Module / Feature | Severity | Priority | Phase Found | Steps to Reproduce | Expected Result | Actual Result | Status | Assigned To | Date Reported | Date Resolved | Evidence (file name or link)
DEF-001 | Profiling form does not scroll to first validation error | Student Profiling | Medium | P2 | System | 1. Open profiling. 2. Leave required field blank. 3. Submit. | Viewport scrolls to first invalid field. | Error shown but user must scroll manually. | Open | [Developer] | 2026-05-15 |  | evidence_DEF-001_profiling_scroll.png
DEF-002 | Dashboard chart legend clipped on narrow viewport | Faculty Dashboard | Low | P3 | System | 1. Open faculty dashboard at 390px width. | Legend readable without overlap. | Legend partially clipped. | Open | [Developer] | 2026-05-15 |  | evidence_DEF-002_chart_legend.png
DEF-003 | Double-submit on concern form creates duplicate records | Concerns | High | P1 | UAT | 1. Submit concern. 2. Double-click submit quickly. | Single concern record. | Duplicate rows created. | Resolved | [Developer] | 2026-05-15 | 2026-05-15 | evidence_DEF-003_duplicate_concern.png
DEF-004 | PDF report blank page when no violations in period | Dashboard / DomPDF | Medium | P2 | System | 1. Generate report with empty violation dataset. | Report states no data or omits section gracefully. | Blank page in PDF. | In Progress | [Developer] | 2026-05-15 |  | evidence_DEF-004_blank_pdf.png
DEF-005 | Student search case-sensitive in violation module | Violations | Medium | P2 | System | 1. Search student with lowercase name. | Case-insensitive match. | No results until exact case matched. | Resolved | [Developer] | 2026-05-15 | 2026-05-15 | evidence_DEF-005_search_case.png
DEF-006 | Notification not received when Reverb stopped | Notifications | Medium | P2 | Integration | 1. Stop Reverb. 2. Approve profile. | Fallback or clear error; notification when service up. | No notification until Reverb restarted. | Deferred | [Developer] | 2026-05-15 |  | evidence_DEF-006_reverb_down.txt
DEF-007 | Admin route typo in account status patch URL | Account Management | Low | P3 | Integration | 1. PATCH account status via documented route. | Status updates. | 404 on mistyped route name (account-mangement). | Open | [Developer] | 2026-05-15 |  | evidence_DEF-007_route_typo.png
DEF-008 | Password reset email not sent in local .env | Authentication | Low | P3 | System | 1. Request password reset without MAIL configured. | User informed mail cannot be sent or log driver shows link. | Silent failure / confusing UX. | Open | [Developer] | 2026-05-15 |  | evidence_DEF-008_mail_config.png