## Sheet1
c | [30 empty] | 7
GANTT CHART
|  | PROJECT TITLE | Knowing Eye |  |  | PROJECT MANAGER |  |  | Saturnino Ancog III | cadientekervy5@gmail.com | [21 empty] | 2026-06-01
|  | PROJECT ADVISER | Lorjohn Raña | START DATE | 2026-04-16 | SYTEM DESIGNER |  |  | Krhisha Marie Cavan | krhishamarieotagancavan@gmail.com | [21 empty] | 2026-06-01 |  |  |  | 2026-06-05
|  | SUBJECT | BSIT Capstone | END DATE | 2026-06-10 | SYSTEM DEVELOPER |  |  | Twixt Jasley Tamera | nexushellstein@gmail.com | [21 empty] | 2026-06-01
|  | COMPANY NAME | WBSMS Team | CURRENT DATE | 2026-06-25 | SYSTEM ARCHITECT |  |  | Kervy Cadiente | cesarancog@gmail.com
[13 empty] | DRIVE FOLDER LINK |  |  |  | https://drive.google.com/drive/folders/1Vc7kXGmtGch1AQoMQbw3BXN14sLyG8on
|  | OVERALL PROGRESS |  |  |  | PHASE PROGRESS |  | P0 | 68.5 |  | 0%
[8 empty] | P1 | 100 |  | 20%
|  | 89.08% | [5 empty] | P2 | 98.75 |  |  |  | DEPLOYMENT LINK (FRONTEND PROTOTYPE) |  |  |  | https://project-knowing-eye.vercel.app/ (NOT UPDATED)
[8 empty] | P3 | N/A |  | 40%
[8 empty] | P4 | N/A
60%
|  | Architecture |  | 98.75 |  |  |  | System Development
|  | Frontend |  | 100 |  |  |  | 98.75% |  |  | 80%
|  | Backend |  | 100
|  | AI Pipeline |  | 100 | [6 empty] | 100%
| !!! |  | WE HAVE ONLY | 9 | DAYS |  | UNTIL |  | OUTLINE SUBMISSION | !!! | [25 empty] | OUTLINE REQUIREMENTS SUBMISSION | [10 empty] | OUTLINE DEFENSE | [31 empty] | TODAY | [5 empty] | OUTLINE SUBMISSION
[12 empty] | P1 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | P2 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | P3 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18
WORK BREAKDOWN STRUCTURE | bar: P1 to 2026-04-16; P2 to 2026-05-03; P3 to 2026-07-18
|  | Phase | Task Title | Owner | Start Date | End Date | Duration (days) | Days Left | Notes | TASK COMPLETION | TASK STATUS | 2026-04-16: WEEK 1; 2026-04-19: WEEK 2; 2026-04-26: WEEK 3; 2026-05-03: WEEK 4; 2026-05-10: WEEK 5; 2026-05-17: WEEK 6; 2026-05-24: WEEK 7; 2026-05-31: WEEK 8; 2026-06-07: WEEK 9; 2026-06-14: WEEK 10; 2026-06-22: WEEK 11; 2026-06-28: WEEK 12; 2026-07-05: WEEK 13; 2026-07-12: WEEK 14
[13 empty] | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S |  | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S |  | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S
|  | 0 | GENERAL TASKS | All | - | - | - | - | Tasks with uncertain durations and schedules | 68.5 | Pending
|  | 0.1 | Completed | All | - | - | - | - |  | 100 | Complete
|  | 0.1.1 | Acquire client contact | All | - | - | - | - |  | 100 | Complete
|  | 0.1.2 | Deliver Email | All | - | - | - | - |  | 100 | Complete
|  | 0.1.3 | System Development Gantt chart insertion | Tamera | - | - | - | - |  | 100 | Complete
|  | 0.1.4 | Establish RRL sheets template | Cadiente & Tamera | - | - | - | - |  | 100 | Complete
|  | 0.1.5 | Catch up to requirements | All | - | - | - | - |  | 100 | Complete
|  | 0.1.6 | Significance of the Study | Cadiente | - | - | - | - |  | 100 | Complete
|  | 0.1.7 | Establish Google Drive | Cadiente | - | - | - | - |  | 100 | Complete
|  | 0.1.8 | revise and polish WBS | Tamera | - | - | - | - |  | 100 | Complete
|  | 0.1.9 | Initialize System Analysis Structure and Beyond | Tamera | - | - | - | - |  | 100 | Complete
|  | 0.2 | Review of Related Literature and Works | Cadiente | - | - | - | - | LACKING (RRL SHEET FIRST) | 75 | Pending
|  | 0.3 | Synthesis | Cadiente & Tamera | - | - | - | - | to clarify | 15 | Pending
|  | 0.4 | Definition of Terms | Cadiente & Tamera | - | - | - | - | to check | 10 | Pending
|  | 0.5 | Chapter 2 methodology | Cadiente & Tamera | - | - | - | - | to check | 45 | Pending
|  | 0.6 | System Planning | Cadiente & Tamera | - | - | - | - | to check | 75 | Pending
|  | 0.7 | System Analysis | Cadiente & Tamera | - | - | - | - | to check | 50 | Pending
|  | 0.8 | System Design | Cadiente & Tamera | - | - | - | - | to check | 50 | Pending
|  | 0.9 | System Testing | Cadiente & Tamera | - | - | - | - | to check | 25 | Pending
|  | 0.1 | System Maintenance | Cadiente & Tamera | - | - | - | - | to check | 25 | Pending
|  | 0.11 | updated references | Cadiente & Tamera | - | - | - | - | to check | 10 | Pending
|  | 0.14 | input WBS components | Ancog | - | - | - | - | to check | 90 | Pending
|  | 0.15 | Input Chapter 2 Components | Cadiente & Tamera | - | - | - | - |  | 0 | Not Started
|  | 0.16 | Insert school bg picture | Cadiente & Tamera | - | - | - | - | to start | 0 | Not Started
|  | 0.17 | Insert school logo | Cadiente & Tamera | - | - | - | - | to start | 0 | Not Started
|  | 1 | PLANNING | All | 2026-04-16 | 2026-05-02 | 17 | -54 |  | 100 | Complete |  | 2026-04-16 | [15 empty] | 2026-05-02
|  | 1.1 | Define core product goals and scope | Tamera | 2026-04-16 | 2026-04-20 | 5 | -66 |  | 100 | Complete |  | 2026-04-16 |  | 2026-04-20
|  | 1.1.1 | Clarify product outcome | Tamera | 2026-04-16 | 2026-04-16 | 1 | -70 | Online exam system with behavior monitoring and reporting | 100 | Complete |  | 2026-04-16
|  | 1.1.2 | Confirm user roles | Tamera | 2026-04-16 | 2026-04-16 | 1 | -66 | examiner/admin, examinee | 100 | Complete |  | 2026-04-16
|  | 1.1.3 | Decide deployment target | Tamera | 2026-04-16 | 2026-04-16 | 1 | -70 | PostgreSQL production, SQLite dev fallback | 100 | Complete |  | 2026-04-16
|  | 1.1.4 | Establish non-functional goals | Tamera | 2026-04-16 | 2026-04-17 | 2 | -70 | Responsive UI, real-time feedback, data integrity | 100 | Complete |  | 2026-04-16
|  | 1.1.5 | Polish & Finalize Chapter 1 | Tamera | 2026-04-16 | 2026-04-17 | 2 | -70 | confirm humanization | 100 | Complete |  |  | 2026-04-17 | 2026-04-18
|  | 1.1.6 | Initialize Chapter 2 | Cadiente & Tamera | 2026-04-18 | 2026-04-20 | 3 | -69 |  | 100 | Complete |  |  |  | 2026-04-18 |  | 2026-04-20
|  | 1.1.6.1 | Open and download related resources | Tamera | 2026-04-18 | 2026-04-18 | 1 | -69 |  | 100 | Complete |  |  |  | 2026-04-18
|  | 1.1.6.2 | Initialize Structure and Format | Cadiente | 2026-04-18 | 2026-04-18 | 1 | -66 | Identify parts | 100 | Complete |  |  |  | 2026-04-18
|  | 1.1.6.3 | Establish Template | Cadiente | 2026-04-18 | 2026-04-18 | 1 | -68 |  | 100 | Complete |  |  |  | 2026-04-18
|  | 1.1.6.4 | Construct | All | 2026-04-19 | 2026-04-20 | 2 | -68 |  | 100 | Complete |  |  |  |  | 2026-04-19 | 2026-04-20
|  | 1.1.7 | Application Logo | Cavan | 2026-04-18 | 2026-04-20 | 3 | -68 |  | 100 | Complete |  |  |  | 2026-04-18 |  | 2026-04-20
|  | 1.1.8 | Establish Client Acceptance | All | 2026-04-18 | 2026-04-20 | 3 | -66 |  | 100 | Complete |  |  |  | 2026-04-18 |  | 2026-04-20
|  | 1.1.8.1 | Construct Email | All | 2026-04-18 | 2026-04-20 | 3 | -66 |  | 100 | Complete |  |  |  | 2026-04-18 |  | 2026-04-20
|  | 1.1.8.2 | define deliverables | All | 2026-04-18 | 2026-04-20 | 3 | -66 | Prototype, Chapter 1 (polished), email | 100 | Complete |  |  |  | 2026-04-18 |  | 2026-04-20
|  | 1.1.8.3 | acquire deliverables | All | 2026-04-18 | 2026-04-20 | 3 | -66 |  | 100 | Complete |  |  |  | 2026-04-18 |  | 2026-04-20
|  | 1.2 | Capture project requirements from documentation | Tamera | 2026-04-16 | 2026-04-20 | 5 | -66 |  | 100 | Complete | [6 empty] | 2026-04-16 |  |  |  | 2026-04-20 | 2026-04-21
|  | 1.2.1 | Map backend responsibilities to feature areas | All | 2026-04-16 | 2026-04-16 | 1 | -66 | auth, exams, session, monitoring, behavior, reports, profile | 100 | Complete | [6 empty] | 2026-04-16
|  | 1.2.2 | Map frontend modules to pages and components | All | 2026-04-17 | 2026-04-17 | 1 | -66 | auth, dashboard, exams, session, monitoring, reports, profile | 100 | Complete | [7 empty] | 2026-04-17
|  | 1.2.3 | Align schema design with API and feature needs | All | 2026-04-18 | 2026-04-19 | 2 | -70 | users, exams, questions, sessions, logs, alerts | 100 | Complete | [8 empty] | 2026-04-18 |  |  | 2026-04-21
|  | 1.2.4 | Confirm monitoring flow | All | 2026-04-20 | 2026-04-20 | 1 | -69 | webcam capture → WebSocket/REST delivery → AI processing → alerts | 100 | Complete
|  | 1.2.5 | Adviser issued revisions | All | 2026-04-20 | 2026-04-20 | 1 | -67 |  | 100 | Complete
|  | 1.2.5.1 | - implement input-output-process (IPO) in objectives | Cadiente & Tamera | 2026-04-20 | 2026-04-21 | 2 | -66 |  | 100 | Complete
|  | 1.2.5.2 | - separate general objectives with specific | Cadiente & Tamera | 2026-04-20 | 2026-04-21 | 2 | -66 |  | 100 | Complete
|  | 1.2.5.3 | - shorten scope | Cadiente & Tamera | 2026-04-20 | 2026-04-21 | 2 | -65 |  | 100 | Complete
|  | 1.2.5.4 | - abolish "this proposed study aims to" | Cadiente & Tamera | 2026-04-20 | 2026-04-21 | 2 | -65 |  | 100 | Complete
|  | 1.2.5.5 | - address thought redundancy in scope | Cadiente & Tamera | 2026-04-20 | 2026-04-21 | 2 | -65 |  | 100 | Complete
|  | 1.2.5.6 | - make scope concise and targeting only major features | Cadiente & Tamera | 2026-04-20 | 2026-04-21 | 2 | -65 |  | 100 | Complete
|  | 1.2.5.7 | - separate scope and limitations | Cadiente & Tamera | 2026-04-20 | 2026-04-21 | 2 | -65 |  | 100 | Complete
|  | 1.2.5.8 | - make scope concise and direct | Cadiente & Tamera | 2026-04-20 | 2026-04-21 | 2 | -65 |  | 100 | Complete
|  | 1.2.5.9 | - make limitations concise and direct | Cadiente & Tamera | 2026-04-20 | 2026-04-21 | 2 | -65 |  | 100 | Complete
|  | 1.2.5.10 | - state: applicable only for institutions that conduct... | Cadiente & Tamera | 2026-04-20 | 2026-04-21 | 2 | -65 |  | 100 | Complete
|  | 1.2.5.11 | - state: no offline capabilities | Cadiente & Tamera | 2026-04-20 | 2026-04-21 | 2 | -65 |  | 100 | Complete
|  | 2 | SYSTEM DEVELOPMENT | All | 2026-05-03 | 2026-05-03 | 1 | -53 |  | 98.75 | Pending | [19 empty] | WEEK 4 S: 2026-05-03; WEEK 10 S: 2026-06-21
|  | 2.1 | System Architecture Design | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 | -53 | Refer to docs > architecture > index.html | 98.75 | Pending | [19 empty] | WEEK 4 S: 2026-05-03; WEEK 4 S: 2026-05-09
|  | 2.1.1 | High-Level Architecture Design | Ancog & Tamera | 2026-05-03 | 2026-05-04 | 2 | -52 |  | 100 | Complete | bar: WEEK 4 S to WEEK 4 M; WEEK 10 S to WEEK 10 S
|  | 2.1.1.1 | Define system architecture | Ancog & Tamera | 2026-05-03 | 2026-05-04 | 2 | -52 | modular monolith or layered architecture | 100 | Complete | bar: WEEK 10 S to WEEK 10 S
|  | 2.1.1.2 | Identify system components | Ancog & Tamera | 2026-05-03 | 2026-05-04 | 2 | -52 | frontend, backend, AI module, database | 100 | Complete | bar: WEEK 10 S to WEEK 10 S
|  | 2.1.1.2.1 | Define frontend component | Ancog & Tamera | 2026-05-03 | 2026-05-04 | 2 | -52 | React + Vite | 100 | Complete | bar: WEEK 4 S to WEEK 4 M; WEEK 10 S to WEEK 10 S
|  | 2.1.1.2.2 | Define backend component | Ancog & Tamera | 2026-05-03 | 2026-05-04 | 2 | -52 | Django + REST + Channels | 100 | Complete | bar: WEEK 4 S to WEEK 4 M; WEEK 10 S to WEEK 10 S
|  | 2.1.1.2.3 | Define AI module for computer vision processing | Ancog & Tamera | 2026-05-03 | 2026-05-04 | 2 | -52 | YOLO, Mediapipe, Facenet/ArcNN | 100 | Complete | bar: WEEK 4 S to WEEK 4 M; WEEK 10 S to WEEK 10 S
|  | 2.1.1.2.4 | Specify database component | Ancog & Tamera | 2026-05-03 | 2026-05-04 | 2 | -52 | PostgreSQL | 100 | Complete | bar: WEEK 4 S to WEEK 4 M; WEEK 10 S to WEEK 10 S
|  | 2.1.1.3 | Define communication protocols | Ancog & Tamera | 2026-05-03 | 2026-05-04 | 2 | -52 | REST APIs, WebSocket | 100 | Complete | bar: WEEK 10 S to WEEK 10 S
|  | 2.1.1.3.1 | Use REST APIs for CRUD operations | Ancog & Tamera | 2026-05-03 | 2026-05-04 | 2 | -52 | confirmed | 100 | Complete | bar: WEEK 4 S to WEEK 4 M; WEEK 10 S to WEEK 10 S
|  | 2.1.1.3.2 | Implement WebSocket for real-time monitoring | Ancog & Tamera | 2026-05-03 | 2026-05-04 | 2 | -52 | confirmed | 100 | Complete | bar: WEEK 4 S to WEEK 4 M; WEEK 10 S to WEEK 10 S
|  | 2.1.1.4 | Design system deployment architecture | Ancog & Tamera | 2026-05-03 | 2026-05-04 | 2 | -52 |  | 100 | Complete | bar: WEEK 10 S to WEEK 10 S
|  | 2.1.1.4.1 | Plan deployment for web-based environment | Ancog & Tamera | 2026-05-03 | 2026-05-04 | 2 | -52 |  | 100 | Complete | bar: WEEK 4 S to WEEK 4 M; WEEK 10 S to WEEK 10 S
|  | 2.1.1.4.2 | Consider cloud hosting options within scope | Ancog & Tamera | 2026-05-03 | 2026-05-04 | 2 | -52 |  | 100 | Complete | bar: WEEK 4 S to WEEK 4 M; WEEK 10 S to WEEK 10 S
|  | 2.1.2 | Backend Architecture Design | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 T to WEEK 4 W; WEEK 10 S to WEEK 10 S
|  | 2.1.2.1 | Define backend framework structure | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 | Django + Django REST + Channels | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.2.1.1 | Set up Django project structure | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 T to WEEK 4 W; WEEK 10 S to WEEK 10 S
|  | 2.1.2.1.2 | Integrate Django REST Framework for APIs | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 T to WEEK 4 W; WEEK 10 S to WEEK 10 S
|  | 2.1.2.1.3 | Configure Channels for WebSocket support | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 T to WEEK 4 W; WEEK 10 S to WEEK 10 S
|  | 2.1.2.2 | Design modular feature-based structure | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 | authentication, exams, sessions, monitoring, reports | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.2.2.1 | Organize features | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 T to WEEK 4 W; WEEK 10 S to WEEK 10 S
|  | 2.1.2.2.2 | Implement service-repository pattern for data access | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 T to WEEK 4 W; WEEK 10 S to WEEK 10 S
|  | 2.1.2.3 | Define service-repository pattern | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.2.3.1 | Create base repository classes for data operations | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 T to WEEK 4 W; WEEK 10 S to WEEK 10 S
|  | 2.1.2.3.2 | Develop service layer for business logic | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 T to WEEK 4 W; WEEK 10 S to WEEK 10 S
|  | 2.1.2.4 | Design API structure and routing | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.2.4.1 | Define RESTful API endpoints for all features | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 T to WEEK 4 W; WEEK 10 S to WEEK 10 S
|  | 2.1.2.4.2 | Implement URL routing and versioning | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 T to WEEK 4 W; WEEK 10 S to WEEK 10 S
|  | 2.1.2.5 | Define authentication and authorization strategy | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.2.5.1 | Implement JWT or session-based authentication | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 T to WEEK 4 W; WEEK 10 S to WEEK 10 S
|  | 2.1.2.5.2 | Set up role-based permissions | Ancog & Tamera | 2026-05-05 | 2026-05-06 | 2 | -50 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 T to WEEK 4 W; WEEK 10 S to WEEK 10 S
|  | 2.1.3 | Frontend Architecture Design | Ancog & Tamera | 2026-05-07 | 2026-05-07 | 1 | -49 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 Th; WEEK 10 S to WEEK 10 S
|  | 2.1.3.1 | Define frontend framework structure | Ancog & Tamera | 2026-05-07 | 2026-05-07 | 1 | -49 | React + Vite | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.3.1.1 | Initialize React application with Vite | Ancog & Tamera | 2026-05-07 | 2026-05-07 | 1 | -49 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 Th; WEEK 10 S to WEEK 10 S
|  | 2.1.3.1.2 | Set up TypeScript for type safety | Ancog & Tamera | 2026-05-07 | 2026-05-07 | 1 | -49 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 Th; WEEK 10 S to WEEK 10 S
|  | 2.1.3.2 | Design component hierarchy and routing | Ancog & Tamera | 2026-05-07 | 2026-05-07 | 1 | -49 |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.3.2.1 | Plan component structure for features | Ancog & Tamera | 2026-05-07 | 2026-05-07 | 1 | -49 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 Th; WEEK 10 S to WEEK 10 S
|  | 2.1.3.2.2 | Implement routing with React Router | Ancog & Tamera | 2026-05-07 | 2026-05-07 | 1 | -49 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 Th; WEEK 10 S to WEEK 10 S
|  | 2.1.3.3 | Define state management approach | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 | -53 |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.3.3.1 | Choose state management solution | Ancog & Tamera | 2026-05-07 | 2026-05-07 | 1 | -49 | Context API or Redux | 100 | Complete | bar: WEEK 4 S; WEEK 4 Th; WEEK 10 S to WEEK 10 S
|  | 2.1.3.3.2 | Design global state for user sessions and monitoring data | Ancog & Tamera | 2026-05-07 | 2026-05-07 | 1 | -49 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 Th; WEEK 10 S to WEEK 10 S
|  | 2.1.3.4 | Plan UI/UX layout and navigation structure | Ancog & Tamera | 2026-05-07 | 2026-05-07 | 1 | -49 |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.3.4.1 | Design responsive layouts for desktop/laptop | Ancog & Tamera | 2026-05-07 | 2026-05-07 | 1 | -49 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 Th; WEEK 10 S to WEEK 10 S
|  | 2.1.3.4.2 | Plan navigation for admin and examinee interfaces | Ancog & Tamera | 2026-05-07 | 2026-05-07 | 1 | -49 |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 Th; WEEK 10 S to WEEK 10 S
|  | 2.1.4 | AI & Monitoring Architecture Design | Ancog & Tamera | 2026-05-08 | 2026-05-08 | 1 | -48 |  | 93.75 | Pending | bar: WEEK 4 S; WEEK 4 F to WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.4.1 | Define AI pipeline architecture | Ancog & Tamera | 2026-05-08 | 2026-05-08 | 1 | -48 |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.4.1.1 | Design pipeline for frame acquisition to analysis output | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 F to WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.4.1.2 | Ensure real-time processing capabilities | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 F to WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.4.2 | Design frame acquisition and preprocessing flow | Ancog & Tamera | 2026-05-08 | 2026-05-08 | 1 | -48 |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.4.2.1 | Implement webcam frame capture | Ancog & Tamera | 2026-05-08 | 2026-05-08 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 F to WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.4.2.2 | Add preprocessing: normalization, resizing, noise reduction | Ancog & Tamera | 2026-05-08 | 2026-05-08 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 F to WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.4.3 | Define model integration strategy | Ancog & Tamera | 2026-05-08 | 2026-05-08 | 1 | -48 | YOLO, CNN, FaceNet/ArcFace | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.4.3.1 | Integrate YOLO for face and posture detection | Ancog & Tamera | 2026-05-08 | 2026-05-08 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 F to WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.4.3.2 | Implement CNN for feature extraction | Ancog & Tamera | 2026-05-08 | 2026-05-08 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 F to WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.4.3.3 | Use FaceNet/ArcFace for facial identity verification | Ancog & Tamera | 2026-05-08 | 2026-05-08 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 F to WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.4.4 | Design real-time processing pipeline | Ancog & Tamera | 2026-05-08 | 2026-05-08 | 1 | -48 |  | 75 | Pending | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.4.4.1 | Optimize for low latency in behavioral analysis | Ancog & Tamera | 2026-05-08 | 2026-05-08 | 1 |  | to confirm | 75 | Pending | bar: WEEK 4 S; WEEK 4 F to WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.4.4.2 | Handle frame buffering and sequential processing | Ancog & Tamera | 2026-05-08 | 2026-05-08 | 1 |  | to confirm | 75 | Pending | bar: WEEK 4 S; WEEK 4 F to WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.4.5 | Define output format for behavioral analysis | Ancog & Tamera | 2026-05-08 | 2026-05-08 | 1 | -48 |  | 87.5 | Pending | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.4.5.1 | Structure outputs for anomaly detection and scoring | Ancog & Tamera | 2026-05-08 | 2026-05-08 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 F to WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.4.5.2 | Format data for backend storage and dashboard visualization | Ancog & Tamera | 2026-05-08 | 2026-05-08 | 1 |  | to confirm | 75 | Pending | bar: WEEK 4 S; WEEK 4 F to WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5 | Database Design | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 | -47 |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5.1 | Identify entities (users, exams, sessions, logs, alerts) | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5.1.1 | Define User entity with roles | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5.1.2 | Define Exam and Question entities | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5.1.2 | Define Session, Log, and Alert entities | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5.2 | Define relational schema and normalization | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5.2.1 | Establish relationships between entities | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5.2.2 | Normalize to reduce redundancy | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5.3 | Establish foreign keys and constraints | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5.3.1 | Implement referential integrity | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5.3.2 | Add validation constraints | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5.4 | Design indexing strategy for performance | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5.4.1 | Index frequently queried fields | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5.4.2 | Optimize for real-time data access | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5.5 | Ensure compatibility (SQLite → PostgreSQL migration) | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5.5.1 | Design schema compatible with both databases | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.1.5.5.2 | Plan migration scripts for production | Ancog & Tamera | 2026-05-09 | 2026-05-09 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2 | Backend Development | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 | -43 |  | 100 | Complete | [19 empty] | WEEK 5 S: 2026-05-10; WEEK 6 F: 2026-05-22
|  | 2.2.1 | Core System Setup | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 S to WEEK 5 W; WEEK 10 S to WEEK 10 S
|  | 2.2.1.1 | Initialize Django project | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.1.1.1 | Set up virtual environment and install dependencies | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 S to WEEK 5 W; WEEK 10 S to WEEK 10 S
|  | 2.2.1.1.2 | Create Django project with proper structure | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 S to WEEK 5 W; WEEK 10 S to WEEK 10 S
|  | 2.2.1.2 | Configure environment variables and settings modules | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.1.2.1 | Define settings for development and production | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 S to WEEK 5 W; WEEK 10 S to WEEK 10 S
|  | 2.2.1.2.2 | Secure sensitive data with environment variables | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 S to WEEK 5 W; WEEK 10 S to WEEK 10 S
|  | 2.2.1.3 | Setup ASGI, WSGI, and Channels | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 |  | ASGI: django (browser > server[daphne] > ASGI app > response) | 100 | Complete | bar: WEEK 4 S; WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.1.3.1 | Configure ASGI for async support | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 |  | modern django | 100 | Complete | bar: WEEK 4 S; WEEK 4 S to WEEK 5 W; WEEK 10 S to WEEK 10 S
|  | 2.2.1.3.2 | Set up Channels for WebSocket handling | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 |  | found mostly in monitoring | 100 | Complete | bar: WEEK 4 S; WEEK 4 S to WEEK 5 W; WEEK 10 S to WEEK 10 S
|  | 2.2.1.4 | Configure middleware and security settings | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.1.4.1 | Implement CORS, CSRF, and security headers | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 S to WEEK 5 W; WEEK 10 S to WEEK 10 S
|  | 2.2.1.4.2 | Add authentication middleware | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 S to WEEK 5 W; WEEK 10 S to WEEK 10 S
|  | 2.2.1.5 | Implement global error handling | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.1.5.1 | Create custom exception handlers | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 S to WEEK 5 W; WEEK 10 S to WEEK 10 S
|  | 2.2.1.5.2 | Implement logging for errors | Ancog & Tamera | 2026-05-10 | 2026-05-13 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 4 S to WEEK 5 W; WEEK 10 S to WEEK 10 S
|  | 2.2.2 | hared Modules Development | Ancog & Tamera | 2026-05-14 | 2026-05-17 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 Th to WEEK 6 S; WEEK 10 S to WEEK 10 S
|  | 2.2.2.1 | Create base repository classes | Ancog & Tamera | 2026-05-14 | 2026-05-17 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.2.1.1 | Develop generic repository pattern | Ancog & Tamera | 2026-05-14 | 2026-05-17 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 Th to WEEK 6 S; WEEK 10 S to WEEK 10 S
|  | 2.2.2.1.2 | Implement CRUD operations | Ancog & Tamera | 2026-05-14 | 2026-05-17 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 Th to WEEK 6 S; WEEK 10 S to WEEK 10 S
|  | 2.2.2.2 | Create base service layer | Ancog & Tamera | 2026-05-14 | 2026-05-17 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.2.2.1 | Define service interfaces | Ancog & Tamera | 2026-05-14 | 2026-05-17 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 Th to WEEK 6 S; WEEK 10 S to WEEK 10 S
|  | 2.2.2.2.2 | Implement business logic abstraction | Ancog & Tamera | 2026-05-14 | 2026-05-17 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 Th to WEEK 6 S; WEEK 10 S to WEEK 10 S
|  | 2.2.2.3 | Implement DTOs and validation utilities | Ancog & Tamera | 2026-05-14 | 2026-05-17 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.2.3.1 | Create data transfer objects | Ancog & Tamera | 2026-05-14 | 2026-05-17 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 Th to WEEK 6 S; WEEK 10 S to WEEK 10 S
|  | 2.2.2.3.2 | Add input validation | Ancog & Tamera | 2026-05-14 | 2026-05-17 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 Th to WEEK 6 S; WEEK 10 S to WEEK 10 S
|  | 2.2.2.4 | Implement timestamp and reusable model mixins | Ancog & Tamera | 2026-05-14 | 2026-05-17 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.2.4.1 | Add timestamp fields to models | Ancog & Tamera | 2026-05-14 | 2026-05-17 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 Th to WEEK 6 S; WEEK 10 S to WEEK 10 S
|  | 2.2.2.4.2 | Create reusable mixins | Ancog & Tamera | 2026-05-14 | 2026-05-17 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 Th to WEEK 6 S; WEEK 10 S to WEEK 10 S
|  | 2.2.2.5 | Create common utility functions | Ancog & Tamera | 2026-05-14 | 2026-05-17 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.2.5.1 | Develop helper functions for common tasks | Ancog & Tamera | 2026-05-14 | 2026-05-17 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 Th to WEEK 6 S; WEEK 10 S to WEEK 10 S
|  | 2.2.2.5,2 | Implement constants and enums | Ancog & Tamera | 2026-05-14 | 2026-05-17 | 4 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 Th to WEEK 6 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3 | Feature Development | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.1 | Authentication & User Management | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.1.1 | Implement user registration API | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.1.2 | Develop login and authentication | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.1.3 | Add password hashing and validation | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.1.4 | Set up role-based access control | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.1.5 | Create profile management APIs | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.2 | Examination Management | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.2.1 | Create exam model and database schema | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.2.2 | Develop question model with options handling | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.2.3 | Implement CRUD APIs for exams and questions | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.2.4 | Implement CRUD APIs for exams and questions | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.2.5 | Configure exam settings (time limits, rules) | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.3 | Session Management | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.3.1 | Implement session initialization and lifecycle | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.3.2 | Add timer and time tracking | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.3.3 | Handle answer submission | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.3.4 | Develop score computation logic | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.3.5 | Manage session termination and result storage | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.4 | Monitoring System | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.4.1 | Implement WebSocket consumer | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.4.2 | Create frame streaming endpoint | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.4.3 | Develop REST fallback endpoint | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.4.4 | Add frame buffering and preprocessing | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.4.5 | Handle real-time data processing | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.5 | Behavior Analysis System | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.5.1 | Create behavior log model and storage | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.5.2 | Implement detection event handling | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.5.3 | Develop scoring algorithm | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.5.4 | Add threshold-based anomaly detection | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.5.5 | Build alert generation system | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.6 | Reporting System | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.6.1 | Develop report generation APIs | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.6.2 | Implement session log retrieval | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.6.3 | Add behavioral analytics computation | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.6.4 | Create export functionality (CSV/PDF) | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.6.5 | Generate summary statistics | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.7 | Profile Management | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.7.1 | Implement user profile retrieval | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.7.2 | Add profile update functionality | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.2.3.7.3 | Handle avatar/image upload | Ancog & Tamera | 2026-05-18 | 2026-05-22 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 5 S to WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.3 | AI Module Development | Ancog & Tamera | 2026-05-23 | 2026-05-27 | 5 | -29 |  | 100 | Complete | [19 empty] | WEEK 6 S: 2026-05-23; WEEK 8 F: 2026-06-05
|  | 2.3.1 | Data Processing | Ancog & Tamera | 2026-05-23 | 2026-05-27 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 6 S to WEEK 7 W; WEEK 10 S to WEEK 10 S
|  | 2.3.1.1 | Frame capture preprocessing | Ancog & Tamera | 2026-05-23 | 2026-05-27 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.3.1.1.1 | Implement frame acquisition from webcam | Ancog & Tamera | 2026-05-23 | 2026-05-27 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 6 S to WEEK 7 W; WEEK 10 S to WEEK 10 S
|  | 2.3.1.1.2 | Add image normalization and resizing | Ancog & Tamera | 2026-05-23 | 2026-05-27 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 6 S to WEEK 7 W; WEEK 10 S to WEEK 10 S
|  | 2.3.1.1.3 | Apply noise reduction and enhancement | Ancog & Tamera | 2026-05-23 | 2026-05-27 | 5 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 6 S to WEEK 7 W; WEEK 10 S to WEEK 10 S
|  | 2.3.2 | Model Integration | Ancog & Tamera | 2026-05-28 | 2026-05-30 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 Th to WEEK 8 S; WEEK 10 S to WEEK 10 S
|  | 2.3.2.1 | Integrate YOLO for detection | Ancog & Tamera | 2026-05-28 | 2026-05-30 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 S; WEEK 10 S to WEEK 10 S
|  | 2.3.2.1.1 | Load and configure YOLO model | Ancog & Tamera | 2026-05-28 | 2026-05-30 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 Th to WEEK 8 S; WEEK 10 S to WEEK 10 S
|  | 2.3.2.1.2 | Implement face and posture detection | Ancog & Tamera | 2026-05-28 | 2026-05-30 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 Th to WEEK 8 S; WEEK 10 S to WEEK 10 S
|  | 2.3.2.2 | Implement CNN feature extraction | Ancog & Tamera | 2026-05-28 | 2026-05-30 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 S; WEEK 10 S to WEEK 10 S
|  | 2.3.2.2.1 | Develop CNN layers for feature extraction | Ancog & Tamera | 2026-05-28 | 2026-05-30 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 Th to WEEK 8 S; WEEK 10 S to WEEK 10 S
|  | 2.3.2.2.2 | Process extracted features for analysis | Ancog & Tamera | 2026-05-28 | 2026-05-30 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 Th to WEEK 8 S; WEEK 10 S to WEEK 10 S
|  | 2.3.2.3 | Integrate FaceNet/ArcFace for identity verification | Ancog & Tamera | 2026-05-28 | 2026-05-30 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 S; WEEK 10 S to WEEK 10 S
|  | 2.3.2.3.1 | Load facial recognition model | Ancog & Tamera | 2026-05-28 | 2026-05-30 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 Th to WEEK 8 S; WEEK 10 S to WEEK 10 S
|  | 2.3.2.3.2 | Implement identity consistency checks | Ancog & Tamera | 2026-05-28 | 2026-05-30 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 Th to WEEK 8 S; WEEK 10 S to WEEK 10 S
|  | 2.3.3 | Behavioral Analysis | Ancog & Tamera | 2026-05-31 | 2026-06-02 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 S to WEEK 8 T; WEEK 10 S to WEEK 10 S
|  | 2.3.3.1 | Facial detection and tracking | Ancog & Tamera | 2026-05-31 | 2026-06-02 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.3.3.1.1 | Detect faces in frames | Ancog & Tamera | 2026-05-31 | 2026-06-02 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 S to WEEK 8 T; WEEK 10 S to WEEK 10 S
|  | 2.3.3.1.2 | Track facial movements over time | Ancog & Tamera | 2026-05-31 | 2026-06-02 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 S to WEEK 8 T; WEEK 10 S to WEEK 10 S
|  | 2.3.3.2 | Head movement analysis | Ancog & Tamera | 2026-05-31 | 2026-06-02 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.3.3.2.1 | Analyze head orientation | Ancog & Tamera | 2026-05-31 | 2026-06-02 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 S to WEEK 8 T; WEEK 10 S to WEEK 10 S
|  | 2.3.3.2.2 | Detect unusual head movements | Ancog & Tamera | 2026-05-31 | 2026-06-02 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 S to WEEK 8 T; WEEK 10 S to WEEK 10 S
|  | 2.3.3.3 | Eye gaze tracking | Ancog & Tamera | 2026-05-31 | 2026-06-02 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.3.3.3.1 | Track eye positions | Ancog & Tamera | 2026-05-31 | 2026-06-02 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 S to WEEK 8 T; WEEK 10 S to WEEK 10 S
|  | 2.3.3.3.2 | Identify gaze direction | Ancog & Tamera | 2026-05-31 | 2026-06-02 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 S to WEEK 8 T; WEEK 10 S to WEEK 10 S
|  | 2.3.3.4 | Posture detection | Ancog & Tamera | 2026-05-31 | 2026-06-02 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.3.3.4.1 | Detect body posture | Ancog & Tamera | 2026-05-31 | 2026-06-02 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 S to WEEK 8 T; WEEK 10 S to WEEK 10 S
|  | 2.3.3.4.2 | Analyze posture changes | Ancog & Tamera | 2026-05-31 | 2026-06-02 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 S to WEEK 8 T; WEEK 10 S to WEEK 10 S
|  | 2.3.3.5 | Suspicious behavior classification | Ancog & Tamera | 2026-05-31 | 2026-06-02 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 S; WEEK 10 S to WEEK 10 S
|  | 2.3.3.5.1 | Classify detected behaviors | Ancog & Tamera | 2026-05-31 | 2026-06-02 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 S to WEEK 8 T; WEEK 10 S to WEEK 10 S
|  | 2.3.3.5.2 | Flag potential anomalies | Ancog & Tamera | 2026-05-31 | 2026-06-02 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 7 S to WEEK 8 T; WEEK 10 S to WEEK 10 S
|  | 2.3.4 | Output & Integration | Ancog & Tamera | 2026-06-03 | 2026-06-05 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 W to WEEK 9 S; WEEK 10 S to WEEK 10 S
|  | 2.3.4.1 | Format structured AI outputs | Ancog & Tamera | 2026-06-03 | 2026-06-05 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.3.4.1.1 | Structure analysis results | Ancog & Tamera | 2026-06-03 | 2026-06-05 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 W to WEEK 9 S; WEEK 10 S to WEEK 10 S
|  | 2.3.4.1.2 | Prepare data for backend consumption | Ancog & Tamera | 2026-06-03 | 2026-06-05 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 W to WEEK 9 S; WEEK 10 S to WEEK 10 S
|  | 2.3.4.2 | Send results to backend services | Ancog & Tamera | 2026-06-03 | 2026-06-05 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.3.4.2.1 | Implement API calls for result transmission | Ancog & Tamera | 2026-06-03 | 2026-06-05 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 W to WEEK 9 S; WEEK 10 S to WEEK 10 S
|  | 2.3.4.2.2 | Handle asynchronous processing | Ancog & Tamera | 2026-06-03 | 2026-06-05 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 W to WEEK 9 S; WEEK 10 S to WEEK 10 S
|  | 2.3.4.3 | Optimize processing latency | Ancog & Tamera | 2026-06-03 | 2026-06-05 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.3.4.3.1 | Tune model performance | Ancog & Tamera | 2026-06-03 | 2026-06-05 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 W to WEEK 9 S; WEEK 10 S to WEEK 10 S
|  | 2.3.4.3.2 | Implement efficient processing pipelines | Ancog & Tamera | 2026-06-03 | 2026-06-05 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 W to WEEK 9 S; WEEK 10 S to WEEK 10 S
|  | 2.3.4.4 | Handle model fallback and failures | Ancog & Tamera | 2026-06-03 | 2026-06-05 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.3.4.4.1 | Add error handling and fallbacks | Ancog & Tamera | 2026-06-03 | 2026-06-05 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 W to WEEK 9 S; WEEK 10 S to WEEK 10 S
|  | 2.3.4.4.2 | Ensure system reliability | Ancog & Tamera | 2026-06-03 | 2026-06-05 | 3 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 W to WEEK 9 S; WEEK 10 S to WEEK 10 S
|  | 2.4 | Frontend Development | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 | -53 |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 S to WEEK 10 S
|  | 2.4.1 | Core Setup | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 S to WEEK 9 T; WEEK 10 S to WEEK 10 S
|  | 2.4.1.1 | Initialize React project with Vite | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.4.1.1.1 | Set up project structure | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 S to WEEK 9 T; WEEK 10 S to WEEK 10 S
|  | 2.4.1.1.2 | Configure Vite build tool | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 S to WEEK 9 T; WEEK 10 S to WEEK 10 S
|  | 2.4.1.2 | Configure routing and navigation | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.4.1.2.1 | Implement React Router | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 S to WEEK 9 T; WEEK 10 S to WEEK 10 S
|  | 2.4.1.2.2 | Design navigation components | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 S to WEEK 9 T; WEEK 10 S to WEEK 10 S
|  | 2.4.1.3 | Setup global state management | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.4.1.3.1 | Choose and configure state management | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 S to WEEK 9 T; WEEK 10 S to WEEK 10 S
|  | 2.4.1.3.2 | Implement global state for app data | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 S to WEEK 9 T; WEEK 10 S to WEEK 10 S
|  | 2.4.1.4 | Configure API client and environment variables | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S to WEEK 10 S
|  | 2.4.1.4.1 | Set up Axios or fetch for API calls | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 S to WEEK 9 T; WEEK 10 S to WEEK 10 S
|  | 2.4.1.4.2 | Manage environment configurations | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 8 S to WEEK 9 T; WEEK 10 S to WEEK 10 S
|  | 2.4.2 | Feature Modules | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.1 | Authentication UI | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.1.1 | Create login and registration forms | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.1.2 | Add input validation and error handling | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.1.3 | Implement session persistence | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.2 | Exam Interface | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.2.1 | Develop exam listing and selection UI | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.2.2 | Implement question rendering and navigation | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.2.3 | Add timer display | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.2.4 | Create answer submission UI | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.3 | Monitoring Interface | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.3.1 | Integrate webcam functionality | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.3.2 | Display live video stream | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.3.3 | Add alert indicators and notifications | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.3.4 | Build monitoring dashboard | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.4 | Behavior Visualization | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.4.1 | Implement behavior score indicators | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.4.2 | Create flagged event list | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.4.3 | Add real-time updates | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.5 | Dashboard | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.5.1 | Design overview statistics cards | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.5.2 | Display recent alerts | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.5.3 | Show activity summaries | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.6 | Reports Interface | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.6.1 | Create report table and filters | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.6.2 | Implement session log viewer | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.6.3 | Add export options | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.7 | Profile Interface | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.7.1 | Develop profile editing forms | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.2.7.2 | Implement avatar upload UI | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 W to WEEK 10 S; WEEK 10 S to WEEK 10 S
|  | 2.4.3 | Shared Components | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 S to WEEK 10 S
|  | 2.4.3.1 | Create layout components (header, sidebar, footer) | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 S
|  | 2.4.3.2 | Implement loading and error states | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 S
|  | 2.4.3.3 | Develop reusable UI components | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 S
|  | 2.4.3.4 | Build custom hooks | Ancog & Tamera | 2026-05-03 | 2026-05-03 | 1 |  |  | 100 | Complete | bar: WEEK 4 S; WEEK 9 S
2
`-
Formulas:
Duration (days) = ABS(DAYS([Start Date],[PROJECT MANAGER])) + 1
Days Left = DAYS([PROJECT MANAGER], TODAY())